## Summary
Metric | Value
Total Iteration | 25
Total Ticket | 16
Ticket Dengan Description | 12
Ticket Tanpa Description | 4
Completion Rate | 75.00%
Missing Rate | 25.00%

## All Tickets
Ticket ID | Iteration | Title | Task Status | Description Status | URL
912 | Scrum 05/01/2026 | Search for system vendor for BPR (CORE BANKING SYSTEM) | Closed | Has Description | http://pm.solusi-ku.id/zentao/task-view-912.html
911 | Scrum 05/01/2026 | Adjust Lender Dashboard API using cached data | Closed | Has Description | http://pm.solusi-ku.id/zentao/task-view-911.html
910 | Scrum 05/01/2026 | Implement CQRS to table v_loan_user_lender_product_summary (slow performance reported by 王茂霖(Morning Wang) | Closed | Has Description | http://pm.solusi-ku.id/zentao/task-view-910.html
909 | Scrum 05/01/2026 | Implement CQRS to table v_loan_user_lender_offering (slow performance reported by 王茂霖(Morning Wang) | Closed | Has Description | http://pm.solusi-ku.id/zentao/task-view-909.html
908 | Scrum 05/01/2026 | Implement CQRS to table v_loan_user_lender_income (slow performance reported by 王茂霖(Morning Wang) | Closed | Has Description | http://pm.solusi-ku.id/zentao/task-view-908.html
907 | Scrum 05/01/2026 | Implement CQRS to table v_loan_user_lender_funding_summary (slow performance reported by 王茂霖(Morning Wang) | Closed | Has Description | http://pm.solusi-ku.id/zentao/task-view-907.html
906 | Scrum 05/01/2026 | Implement CQRS to table v_loan_user_lender_funding (slow performance reported by 王茂霖(Morning Wang) | Closed | Has Description | http://pm.solusi-ku.id/zentao/task-view-906.html
920 | Scrum 12/01/2026 | Remapping Risk Register on management tools | On Progress | Missing Description | http://pm.solusi-ku.id/zentao/task-view-920.html
922 | Scrum 12/01/2026 | Create Report Assesment Core Banking System | Resolved | Missing Description | http://pm.solusi-ku.id/zentao/task-view-922.html
917 | Scrum 12/01/2026 | Implement CQRS for Funding History Monitoringx | Resolved | Has Description | http://pm.solusi-ku.id/zentao/task-view-917.html
916 | Scrum 12/01/2026 | Funding History Monitoring Integration on Lender Dashboard | Resolved | Has Description | http://pm.solusi-ku.id/zentao/task-view-916.html
914 | Scrum 12/01/2026 | UI for Activation of Existing RDL investors on Backoffice | Resolved | Has Description | http://pm.solusi-ku.id/zentao/task-view-914.html
913 | Scrum 12/01/2026 | API for Activation of Existing RDL investors on Backoffice | Resolved | Has Description | http://pm.solusi-ku.id/zentao/task-view-913.html
919 | Scrum 12/01/2026 | Implement Jira for management tools | Closed | Missing Description | http://pm.solusi-ku.id/zentao/task-view-919.html
918 | Scrum 12/01/2026 | Create action plan for ISO/IEC 27001:2022 audit findings | Closed | Missing Description | http://pm.solusi-ku.id/zentao/task-view-918.html
915 | Scrum 12/01/2026 | Create a Funding History Monitoring API on the Lender Dashboard | Closed | Has Description | http://pm.solusi-ku.id/zentao/task-view-915.html

## Missing Description
Ticket ID | Iteration | Title | Task Status | URL
920 | Scrum 12/01/2026 | Remapping Risk Register on management tools | On Progress | http://pm.solusi-ku.id/zentao/task-view-920.html
922 | Scrum 12/01/2026 | Create Report Assesment Core Banking System | Resolved | http://pm.solusi-ku.id/zentao/task-view-922.html
919 | Scrum 12/01/2026 | Implement Jira for management tools | Closed | http://pm.solusi-ku.id/zentao/task-view-919.html
918 | Scrum 12/01/2026 | Create action plan for ISO/IEC 27001:2022 audit findings | Closed | http://pm.solusi-ku.id/zentao/task-view-918.html